## Tech Stack
🛠 PurgeKit — Tech Stack
v3.4 · MIT License · TeamExyKings
# | Layer | Technology | Version | Purpose | License | Notes
1 | Language | Python | 3.11+ | Core application logic | PSF | Main programming language
2 | UI Framework | CustomTkinter | 6.0+ | Modern dark-theme GUI widgets | MIT | github.com/TomSchimansky/CustomTkinter
3 | Image | Pillow | 10.0+ | Icon generation, image handling | HPND | Fork of PIL — open license
4 | Notifications | winotify | 1.1+ | Windows 10/11 toast notifications | MIT | Windows-only
5 | Charts | matplotlib | 3.7+ | Space saved history bar chart | PSF | Only used in history panel
6 | Tray | pystray | 0.19+ | System tray icon support | LGPL3 | Planned for v4.0
7 | Packaging | PyInstaller | 6.0+ | Compile to standalone .exe | GPL+ | Bootloader exception allows free distribution
8 | Installer | Inno Setup | 6.7+ | Windows Setup .exe builder | ISL | Free for commercial use
9 | SW Updater | winget (Microsoft) | Built-in | Scan & update installed apps | Windows | Official Windows Package Manager
10 | Registry | winreg | stdlib | Auto-start, startup programs | PSF | Python standard library
11 | Networking | urllib | stdlib | GitHub API version checks | PSF | Python standard library
12 | Subprocess | subprocess | stdlib | Run winget, schtasks, system cmds | PSF | Python standard library
13 | Storage | JSON | stdlib | Config, history, whitelist files | PSF | Stored in %APPDATA%\PurgeKit\
14 | Hashing | hashlib / SHA-256 | stdlib | PIN lock security | PSF | PIN never stored as plain text
15 | Build CI | GitHub Actions | N/A | Future CI/CD automation | Free | Planned for v4.0

## Feature Tracker
✅ PurgeKit — Feature Tracker
All features across all versions
# | Version | Feature | Description | Phase | Status | Priority | Notes
1 | v1.0 | BAT Script Cleaner | Initial batch script for temp/cache cleaning | Core | Done | High | Replaced by GUI in v2.0
2 | v1.1 | Y/N Per Step | User prompted before each cleaning step | UX | Done | High
3 | v1.1 | 3-Technique Force Delete | robocopy→takeown→reboot pending cascade | Core | Done | High | Handles locked files
4 | v2.0 | Python GUI | CustomTkinter dark-theme GUI | Core | Done | High
5 | v2.0 | Progress Bar | Visual progress during purge | UX | Done | Medium
6 | v2.0 | Log Files | Structured log saved to Downloads\PurgeKit\Logs\ | Core | Done | Medium
7 | v2.1 | Per-Drive Disk Cleanup | Auto-detect drives, run cleanmgr per drive | Core | Done | High
8 | v2.1 | About Tab | App info, GitHub link, version | UX | Done | Low
9 | v2.2 | Compact/Spacious Toggle | Switch between tab and sidebar layout | UX | Done | Medium
10 | v2.2 | Service Worker Cache | Chrome + Edge service worker cache clearing | Browser | Done | Medium
11 | v3.0 | 29 Languages | Full UI translation in 29 world languages | i18n | Done | High | JSON-based, live switch
12 | v3.0 | 3 Themes | Green/Blue/Purple accent, live apply | UX | Done | Medium
13 | v3.0 | First Run Wizard | Language→Theme→Options on first launch | UX | Done | High
14 | v3.0 | PIN Lock | 6-digit PIN, SHA-256, 3-attempt lockout | Security | Done | Medium
15 | v3.0 | Dry Run Mode | Preview deletions without actually deleting | Safety | Done | High
16 | v3.0 | Junk Scanner | Scan+rank junk folders by size, Clean Selected | Core | Done | High
17 | v3.0 | Scheduler | Weekly/monthly auto-purge via Task Scheduler | Automation | Done | Medium
18 | v3.0 | Whitelist | Exclude folders from all cleaning | Safety | Done | Medium
19 | v3.0 | Remember Selection | Last task choices restored on reopen | UX | Done | Medium
20 | v3.0 | CLI Silent Mode | PurgeKit.exe --silent for automation | Automation | Done | Low
21 | v3.1 | Sidebar Navigation | Spacious mode: left sidebar with active highlight | UX | Done | Medium
22 | v3.1 | Size Per Row | Background scan shows each folder size | UX | Done | Medium
23 | v3.1 | Taskbar Icon Fix | SetCurrentProcessExplicitAppUserModelID | UX | Done | Low
24 | v3.2 | Auto-Update | Download+install+relaunch from GitHub releases | Core | Done | High | Works only with .exe
25 | v3.3 | System Info Panel | RAM, disk per-drive, OS, uptime, processor | UX | Done | Medium
26 | v3.3 | Zoom/Discord/WhatsApp | New cache paths for popular apps | Core | Done | Medium
27 | v3.3 | Windows Defender Cache | Clears Defender scan history | Core | Done | Medium
28 | v3.3 | Donate Button | PayPal link in About tab | UX | Done | Low
29 | v3.4 | Software Updater | winget-based scan & update for all installed apps | Core | Done | High | Free, no 3rd-party DB
30 | v3.4 | Social Media Kit | Cards, captions, hashtags, YT assets | Marketing | Done | Low
31 | v4.0 | System Tray | Minimize to tray, quick actions | UX | Planned | Medium
32 | v4.0 | Portable Mode | Run from USB, no install needed | Core | Planned | Low
33 | v4.1 | Secure Delete | DoD 3-pass wipe before deletion | Security | Planned | Low
34 | v4.2 | PDF Report Export | Export run log as formatted PDF | Reporting | Planned | Low

## Issue Tracker
🐛 PurgeKit — Issue Tracker
Track bugs, fixes, and improvements
# | Version | Type | Severity | Title | Description | Status | Fixed In | Notes
1 | v2.0 | Bug | High | Admin relaunch loop | UAC relaunch caused infinite loop on some systems | Fixed | v2.0 | Added is_admin() check
2 | v2.1 | Bug | High | Drive detection missing D: | GetDriveTypeW excluded removable/network drives | Fixed | v2.2 | Now checks total>0 instead
3 | v3.0 | Bug | High | tab_length not supported | CTkTabview does not accept tab_length argument | Fixed | v3.1 | Removed unsupported arg
4 | v3.0 | Bug | Medium | _compute_task_sizes missing | Method called before class init in compact mode | Fixed | v3.1.1 | Inserted by line number
5 | v3.0 | Bug | Medium | Scan results not clearing | Old scan results remained after new scan started | Fixed | v3.1.2 | Clear on scan start
6 | v3.0 | Bug | Medium | Startup tab flicker | Enable/disable refreshed immediately causing flicker | Fixed | v3.1.2 | 400ms delay before refresh
7 | v3.1 | Bug | High | _panel_sysinfo AttributeError | Method inserted after call in compact layout build | Fixed | v3.3 | Inserted by line number idx
8 | v3.1 | Bug | Medium | Update checker false positive | CURRENT_VERSION stuck at 3.0, always showed update | Fixed | v3.1.6 | Synced to APP_VERSION
9 | v3.1 | Bug | Medium | App icon showing Python duck | iconbitmap not persistent for compiled exe | Fixed | v3.1.6 | Save to %APPDATA% + AppUserModelID
10 | v3.2 | Bug | Low | Inno Setup code 740 error | Post-install run needed elevation, failed silently | Fixed | v3.3 | Added runascurrentuser flag
11 | v3.3 | Bug | Medium | Version shows 3.1 in About | APP_VERSION not updated consistently across files | Fixed | v3.3.1 | All 4 version locations updated
12 | v3.3 | Improvement | Low | History tab always empty | History tab showed no data, wasted tab space | Fixed | v3.1.4 | Tab removed
13 | v3.3 | Improvement | Low | Startup tab not functional | Enable/disable not properly wired, tab not useful | Fixed | v3.1.3 | Tab removed
14 | v3.3 | Improvement | Low | Tab name lowercase sysinfo | Tab showed "tab_sysinfo" instead of "SysInfo" | Fixed | v3.3.1 | Updated all 29 lang files
15 | v3.4 | Feature Req | Medium | Software Updater | Users want to update apps from PurgeKit | Done | v3.4 | Built with winget
16 | v4.0 | Feature Req | Medium | System Tray | Minimize to tray instead of closing | Planned | v4.0 | pystray library ready
17 | v4.0 | Feature Req | Low | Portable Mode | Run from USB with local config save | Planned | v4.0
18 | v4.1 | Feature Req | Low | Secure Delete | DoD 3-pass overwrite before delete | Planned | v4.1
19 | Open | Bug | Low | winget timeout on slow PCs | winget upgrade can take >90s on slow machines | Open |  | Increase timeout or add cancel
20 | Open | Improvement | Low | Theme not saved in wizard | Theme change in wizard needs app restart to fully apply | Open |  | Investigate CTk theme reload

## GitHub
🐙 PurgeKit — GitHub Reference
Repository links, release history, and contribution guide
Resource | URL | Notes
Repository | https://github.com/yashwanthramsomireddy/PurgeKit | Main source code
Releases | https://github.com/yashwanthramsomireddy/PurgeKit/releases | Download PurgeKit.exe + Setup.exe
Issues | https://github.com/yashwanthramsomireddy/PurgeKit/issues | Bug reports and feature requests
Pull Requests | https://github.com/yashwanthramsomireddy/PurgeKit/pulls | Contributions
CHANGELOG.md | https://github.com/yashwanthramsomireddy/PurgeKit/blob/main/CHANGELOG.md | Full version history
README.md | https://github.com/yashwanthramsomireddy/PurgeKit/blob/main/README.md | Project readme
GitHub API | https://api.github.com/repos/yashwanthramsomireddy/PurgeKit/releases/latest | Used for auto-update check
winget install | https://aka.ms/getwinget | Get winget for Windows 10
Release History | Tag | Highlights
v1.0 | v1.0 | Initial .bat release
v1.1 | v1.1 | Force delete, activity history
v2.0 | v2.0 | Python GUI
v2.1 | v2.1 | Per-drive cleanup
v2.2 | v2.2 | Compact mode, new caches
v3.0 | v3.0 | 29 languages, wizard, PIN
v3.1 | v3.1 | Sidebar, scan clean, size labels
v3.2 | v3.2 | Auto-update
v3.3 | v3.3 | New caches, System Info, donate
v3.3.1 | v3.3.1 | Version fix, icon, Inno fix
v3.4 | v3.4 | Software Updater, social kit, docs

## Donation
💛 PurgeKit — Donation & Support
Support the project and keep it free for everyone
Platform | Link / Details | Handle | Status
PayPal | https://www.paypal.com/paypalme/yash92duster | yash92duster | Active
GitHub Sponsors | https://github.com/sponsors/yashwanthramsomireddy | yashwanthramsomireddy | Setup Pending
Ko-fi | https://ko-fi.com | Setup when ready | Planned
Buy Me a Coffee | https://buymeacoffee.com | Setup when ready | Planned
Why Donate?
PurgeKit is and will always remain 100% free and open source.
Donations help cover time spent on development, testing, and maintaining the project.
Every contribution — big or small — is deeply appreciated.
You can also contribute by starring the repo, reporting bugs, or submitting pull requests!